## import
Title | Demand Number | Initiative Name | Program Project | Technical Manager | Agentic Engineer | TurnKey Project | Description | Received Start Date | Expected Completion Date | Technology Type | Technology | Status | Stage | Stage Level | Progress Pct | Division | Total Process | Agentic Process | AI Transformation Pct | Human On The Loop | Base Line Time | Time After AI | Time Saving Hours | Time Saving Pct | Total FTE Saving | Cost Saving FTE | Productivity Pct | Other Cost Saving | Total Cost Saving | Comment
Automation of DSC File Transfer | DR20-0051 | Adhoc | Project | Ayub | Indus Technology | Yes | Automates downloading, organizing, and uploading ITRon system reports to BDA platform. This solution streamlines the file transfer process, reducing manual intervention and improving operational efficiency.​ | 2025-09-08 00:00:00 | 16/06/26 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.15 | DP | 5 | 3 |  |  | 1760 | 587 | #REF! | #REF! | #REF! | #REF! | #REF! | 300000 | #REF!
One to One Meeting Tracker |  | Adhoc | Initiative Internal | Mahmoud | Delphi | Yes | Application for automated scheduling and tracking of one-to-one meetings, integrated with Microsoft 365. Enables efficient meeting management, documentation of outcomes, and follow-up on action items for enhanced productivity and accountability.​ |  | TBD | Automation | Power Platform | Inprogress | Security Approval | Pre ISRP | 0.8 | I&TF | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Cyber360 Portal | DR20_0534 | Adhoc | Project | Ayub | Alpha Data | Yes | Application for automated scheduling and tracking of one-to-one meetings, integrated with Microsoft 365. Enables efficient meeting management, documentation of outcomes, and follow-up on action items for enhanced productivity and accountability.​ | 2024-12-02 00:00:00 | 2025-08-11 00:00:00 | Automation | Power Platform | Completed | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Cyber360 Portal Phase 2 | DR20_0534 | Adhoc | Enhancment | Ayub | Alpha Data | Yes | Application for automated scheduling and tracking of one-to-one meetings, integrated with Microsoft 365. Enables efficient meeting management, documentation of outcomes, and follow-up on action items for enhanced productivity and accountability.​ | 2025-12-12 00:00:00 | 2026-03-20 00:00:00 | Automation | Power Platform | Completed | completed | Production | 0.8 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Employee ePass & Violation Management System | DR23_0115 | Adhoc | Project | Ayub | Finnese Technology | Yes | Automates employee gate pass requests and issuance for Generation offices. The system will streamline the current manual process, improve security compliance and provide digital tracking of employee access​ | 2025-08-14 00:00:00 | 2026-05-25 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.45 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CAA Automation phase1 | DR23_0551 | Adhoc | Project | Ayub | Ashwin | No | CAA Phase 1 focuses on the automation and centralization of security approval processes across the organization. The project aims to eliminate manual approval handling by implementing a unified platform that consolidates all security-related requests, workflows, and approvals into a single system. This ensures improved visibility, faster turnaround times, standardized governance, and better auditability of security decisions while aligning with enterprise compliance requirements. | 2024-08-01 00:00:00 | 2025-08-19 00:00:00 | Automation | Power Platform | Completed | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CAA Automation Phase 1Enhancment +Phase2 | DR23_0551 | Adhoc | Enhancment | Ayub | Ashwin | No | CAA Phase 2 builds on the foundation established in Phase 1 by introducing advanced enhancements to the security approval framework. This phase focuses on improving workflow efficiency, incorporating dynamic approval logic, expanding integration with enterprise systems, and enhancing user experience. The objective is to enable intelligent, scalable, and policy-driven approval processes with improved tracking, reporting, and decision-making capabilities. | 2025-08-19 00:00:00 | 2026-04-30 00:00:00 | Automation | Power Platform | Inprogress | UAT | Pre ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Case and Dispute Management Process​ | DR24_0867 | Adhoc | Project | Saeed | Alpha Data | Yes | The Case and Dispute Management Automation Solutions (Case From DEWA and Case Against DEWA) project for Moro Hub/DEWA aims to serve as central hub for all legal communication within DEWA and external law firms. It helps in initiating, tracking all cases efficiently.​ |  | TBD | Automation | Power Platform | Inprogress | Development / Security Approval |  | 0.2 | Legal |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
COE Platform | DR25-0347 | COE Platform | Project | Jamil | Tharakeswar | No | The COE Platform is designed as a centralized Center of Excellence to monitor and drive organizational adoption of technologies, including AI and Microsoft ecosystem solutions. The platform provides consolidated insights into adoption metrics across technology, people, and divisions, enabling leadership to track performance, usage trends, and maturity levels. It integrates dashboards, KPIs, and data sources to support real-time visibility, collaboration, and strategic decision-making across the enterprise |  | 2026-08-30 00:00:00 | Automation | Power Platform; Power BI | Inprogress | Development | Pre ISRP | 0.66 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Migration of BMC Helix Control-M to Microsoft Power Platform |  | Adhoc | Project | Jamil | Ashwin | No | Control Hub is a centralized platform designed to manage, monitor, and control system jobs and processes across multiple applications and environments in DEWA. It provides real-time visibility into job execution, status tracking, failure alerts, and operational insights. |  | TBD | Automation | Power Platform | Inprogress | Initiation | Requierment Gathering | 0 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
KOFAX Upgrade and DR creation | DR25_0126 | Adhoc | Project | Ayub | Indus Technology | Yes | The project aims to upgrade Kofax KTA and RPA, integrate Ping ID and LDAP, and implement robust disaster recovery architecture, ensuring operational resilience, security compliance, and seamless migration to Microsoft Power Platform for future scalability.​ | 2025-11-04 00:00:00 | 2026-05-30 00:00:00 | Automation | KOFAX Platform | Inprogress | UAT | Pre ISRP | 0.8 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Refreshment Portal |  |  | Project | Mahmoud | Sumit/Subhash | No | A centralized portal to manage and maintain all refreshment-related data and requests for senior staff by the GA team. |  | 2026-07-01 00:00:00 | Automation | Power Platform + Vibe coding | Inprogress | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Digital Feature Management | DR23_0553 | Adhoc | Project | Nida | TechMantra Technology | Yes | Creates an AI-powered portal for all DEWA's digital assets, allowing users to search for product information and specifications. The portal uses OpenAI to generate natural language descriptions of product features and includes a dashboard for management to track product usage and performance.​ | 2025-06-02 00:00:00 | 2026-05-01 00:00:00 | AI Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.5 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Automation of Attendance Fix IN/OUT Error | - | Alhasbah | Alhasbah | Ayub | Alpha Data | Yes | The HR Automation (Fixing IN & OUT & At work despite full day Absence) project for DEWA aims to reduce the time-consuming process of manual data entry and cleansing in SAP, thereby enhancing efficiency and enabling a stronger focus on the daily evaluation of employee absences. ​ | 2025-12-12 00:00:00 | 2026-05-06 00:00:00 | Automation | Power Platform | Inprogress | Security Approval | Pre ISRP | 0.75 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Performance Review Management System (PRMS) for TP | DR24_0802 | Adhoc | Project | Mahmoud | Ashwin | No | PRMS (Performance Review Management System) for Transmission Power is designed to streamline and automate the end-to-end performance evaluation process within the Transmission Power division. The system enables structured performance tracking, standardized review workflows, and centralized data management, ensuring consistency and transparency across evaluations. It incorporates automated report generation. |  | 2026-09-30 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.35 | TP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Dubai Data Ingestion | DR23_0530 | Adhoc | Project | Mahmoud | Ducont | Yes | Files are currently placed in multiple locations at different times, making timely uploads to the DDA SFTP portal difficult. The new solution uses Kofax RPA to automate the process, ensuring seamless integration, timely reporting, and robust error handling with audit logs.​ | - | Completed | Automation | KOFAX Platform | Completed | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
TEC | DR25_000231 | Kofax Migration | Project | Priyanka | Prem | No | Daily Measures raised by TP and W&C Divisions are submitted through a multi‑level validation and approval workflow. Once approved by all stakeholders, the measures are sent to the Executive Council Dashboard via SAP integration for executive visibility. | 2026-01-12 00:00:00 | 2026-08-17 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.6 | TP, W&C,P&WP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Shams Dubai Email subscription | DR25_000231 | Kofax Migration | Project | Priyanka | Akash | No | Centralized Email Subscription Management process for handling subscribe, confirmation, unsubscribe, and reporting activities. Public users submit subscription requests through an external website, which are processed using automated workflows. | 2026-08-01 00:00:00 | 2026-04-30 00:00:00 | Automation | Power Platform | Inprogress | UAT | Pre ISRP | 0.9 | DP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
WCA | DR25_000231 | Kofax Migration | Project | Priyanka | Anjana | No | The WCA creation is to generate the WCA for the Under Frequency Load Shedding (UFLS) process in SAP to facilitate quarterly substation field visits. These visits will be conducted at all applicable 132/11 kV substations by the DFO team under the DP Division. | 2026-02-17 00:00:00 | 2026-08-17 00:00:00 | Automation | Power Platform | Inprogress | UAT | Pre ISRP | 0.9 | DP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Wesal | DR25_000231 | Kofax Migration | Project | Priyanka | Akash | No | The Wesal system serves as a communication tool between DEWA and its employees by sending personalized text messages and emails for special occasions such as graduations, marriages, new births, and condolence notifications. The new solution will digitize the submission workflow using Power Apps and automate approval routing, email notifications, and task assignments through Power Automate. | 2026-09-03 00:00:00 | 2026-08-17 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.8 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Capacity plan integration with estimrar |  | Adhoc | Project | Mahmoud | Sumit/Subhash | No |  |  | 2026-10-01 00:00:00 | Automation | Power Platform + Vibe coding | Inprogress | Initiation | Requierment Gathering | 0.1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Catering Service Request |  | Adhoc | Project | Mahmoud | Sumit/Subhash | No | Track, manage, and report all SAP initiatives to stakeholders through a centralized dashboard with real-time updates, approvals, and insights. |  | 2026-04-30 00:00:00 | Automation | Power Platform | Inprogress | Security Approval | Post ISRP | 0.9 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Automation of Facility Management |  | Adhoc | Project | Mahmoud | Sumit/Subhash | No | Centralized system will track senior staff refreshment requests, approvals, and inventory management, reducing manual effort, errors, paperwork, and improving control, transparency, and reporting efficiency. |  | 2026-04-30 00:00:00 | Automation | Power Platform | Inprogress | security Approval | Post ISRP | 0.9 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
D2D | DR24-0786 | D2D | Project | Mahmoud | Asjad/Athish/Mohammad Sajid | No | The proposed Demand to Delivery solution aims to consolidate all functionalities into a single, centralized platform that enables seamless integration between demand intake, evaluation, planning, execution, monitoring, and closure. This unified approach will improve transparency, enhance cross-functional collaboration, standardize governance controls, and provide real-time reporting and analytics across all stages. Ultimately, the system will serve as a single source of truth, ensuring improved traceability, optimized resource utilization, accelerated delivery timelines, and stronger alignment with organizational strategic objectives. | 2025-11-01 00:00:00 | 20/12/2026 | AI Automation | Power Platform +Copilot Studio | Inprogress | Development | Pre ISRP | 0.2 | I&TF | 3 | 15 | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Absente HR Report Automation | DR25_000231 | Kofax Migration | Alhasbah | Priyanka | Sumathi M | No | This project will enable HR departments within DEWA to access the SAP system and generate three reports related to the attendance control process. The required reports will be produced through a streamlined workflow where the system retrieves all necessary attendance data and makes it available for processing. The output will then be shared and used to update the relevant records and support attendance monitoring activities efficiently. | 19/01/2026 | 2026-08-17 00:00:00 | Automation | Power Platform | Completed | completed | Live | 1 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Time Evaluation HR Report Automation | DR25_000231 | Kofax Migration | Alhasbah | Priyanka | Rakul | No |  | 19/01/2026 | 2026-08-17 00:00:00 | Automation | Power Platform | Completed | completed | Live | 1 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
OverTime HR Report Automation | DR25_000231 | Kofax Migration | Alhasbah | Priyanka | Rakul | No |  | 19/01/2026 | 2026-08-17 00:00:00 | Automation | Power Platform | Completed | completed | Live | 1 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
ADOP-Backend flows |  | Adhoc | Project Support | Mahmoud | mahmoud | No |  | - | Completed | Automation | Power Automate |  | completed | Production | 1 | DP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Microsoft license assignment |  |  | Alhasbah | Priyanka | Priyanka | No | Microsoft License Assignment Automation streamlines the entire license assignment process. Once the Khatamatech approval is completed, the automation is triggered automatically and adds the user to the security group associated with the required Microsoft license. | - | TBD-On Hol | Automation | Power Platform |  | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
DMC Agent |  |  | POC | Ricardo | Sofia | No | Marketing agent capable of dynamically populating requests for marketing material like e-shorts in a conversational way, taking in consideration a number of validations. After all information is collected, request is sent to marketing team to take action. |  | 2026-03-06 00:00:00 | AI Agent | Copilot Studio | Inprogress | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Copilot Analytics Platform |  |  | Initiative Internal | Ricardo | Alexandre | No | Automa | - | Completed | AI Agent | Power Platform; Power BI |  | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
AI Adoption Agent |  |  | Initiative Internal | Ricardo | Alexandre | No | Power Automate flow triggered by forms submission that populates missing columns in the result Excel | - | Completed | AI Agent | Power Automate |  | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Teams Daily Copilot Usage |  |  | Initiative Internal | Ricardo | Ricardo | No | Extract daily Copilot usage, generate engaging message for users not using Copilot, send on Teams. | - | Completed | AI Automation | Power Automate |  | completed | Production | 1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Certificate genration |  |  | Alhasbah | Ricardo | Ricardo | No | Build automation to populate Sharepoint List with meeting details and generate/send certificates by email. |  | 17/4/2026 | AI Agent | Power Platform | Inprogress | Development | Pre ISRP | 0.85 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Supplier Agent |  |  | Alhasbah | Ricardo | Alexandre | No | AI automation to reply to new e-mails in the SRM inbox. Serves as the first point of contact with any internal or external user that contacts the SRM e-mail. Currently, we are reducing the workload of the supplier team by gathering all the new e-mails in a comprehensive BackOffice and detailing all the important characteristics and user’s feedback. Finally, we generate a response through dedicated categorization to each new e-mail received.​ |  | 2026-05-05 00:00:00 | AI Agent | Power Platform +Copilot Studio | Inprogress | UAT | Post ISRP | 0.9 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Khadamatech Agent |  |  | POC | Ricardo | Sofia | No | Copilot Studio agent that enables employees to open Khadamatech forms by dynamically populating in a conversational way. |  |  | AI Agent | Copilot Studio | Inprogress | Development | Pre ISRP | 0.75 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
MEMO summrization |  |  | POC | Ricardo | Alexandre | No | Copilot Studio agent capable of reading employee's memo, summarizing with the vital information and enable employee to take action. | - | Completed | Automation | Copilot Studio |  | Development | Pre ISRP | 0.8 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Datahub Platfrom |  |  | Project | Mahmoud | Sumit/Subhash | No | Datahub is an initiative by the Data Governance team to centrally track and manage all datasets, champion management, entities, and daily external data source transactions across the organization. |  | 2026-05-15 00:00:00 | Automation | Power Platform + Vibe coding | Inprogress | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
DCC AI Agent |  |  | Alhasbah | Ricardo | Alexandre | No | AI platform to categorize emails coming to DCC shared inbox and auto-reply depending on the category. | - | Completed | AI Agent | Power Platform |  | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Gen AI- CV Screening for HR |  | Alhasbah | Alhasbah | Saeed | Sofia | No | AI platform to match candidate CVs against Job Descriptions in order to make a pre-selection of candidates to further interview. |  | 2026-03-06 00:00:00 | AI Automation | Power Platform +Copilot Studio | Inprogress | completed | Production | 0.95 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Marketing Tracker portal | DR26-66 | Adhoc | Project | Mahmoud | Priyanka/ Prem | No | The Marketing Campaign Manager App is a centralized digital platform developed for the Marketing & Communication team to plan, manage, track, and monitor marketing campaigns and sub‑campaigns across daily, monthly, and quarterly cycles. | 2026-02-02 00:00:00 | Completed | Automation | Power Platform | Inprogress | UAT | Post ISRP | 0.9 | S&CG |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Sap Board - Phase1 | - | Adhoc | Project | Mahmoud | Priyanka/Rakul | No | Track, manage, and report all SAP initiatives to stakeholders through a centralized dashboard with real-time updates, approvals, and insights. | 18/02/2026 | Completed | AI Agent | Power Platform | Inprogress | completed | Pre ISRP | 1 | SAP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
MD & CFO Finance Project | DR26-218 | Adhoc | Project | Jamil | Priyanka/Prem | No | The MD & CFO Finance Project is designed to provide a secure, centralized platform for Finance teams to submit, review, and approve financial data and KPIs through a controlled approval workflow. |  | 2026-05-30 00:00:00 | Automation | Power Platform | Inprogress | UAT | Post ISRP | 0.9 | Finance |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Sap Board-Phase 2 | - | Adhoc | Project | Mahmoud | Priyanka/Rakul | No | Track, manage, and report all SAP initiatives to stakeholders through a centralized dashboard with real-time updates, approvals, and insights and integration with other data sources and application. |  | 2026-10-30 00:00:00 | Automation | Power Platform | Inprogress | Initiation | Requierment Gathering | 0.1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Vendor Bank Details |  |  | Alhasbah | Ricardo + Saeed | Alexandre | No | The Vendor Bank Details Platform will streamline bank detail submissions using Power Platform and AI. Vendors can attach supporting documents through a CRM interface, while Power Automate triggers OCR-based data extraction to automatically read and populate bank detail fields. AI validation ensures accuracy of account numbers, IBAN, and routing details, with all data securely stored in Dataverse for efficient processing and approval workflows. |  | TBD | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.7 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Ai Incident Management - Phase 1 |  | Adhoc | Project | Ayub | Ashwin | No | The AI Incident Management Logs project aims to establish a centralized, structured, and auditable mechanism for logging, tracking, and analyzing incidents related to AI platforms and services (including AI OS, Agentic AI, and Power Platform use cases). The initiative supports operational stability, governance, and data-driven decision-making across AI deployment​ | 2026-04-19 00:00:00 | 2026-06-20 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.7 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Integration of Estimrar list with capacity plan and availability reports |  |  | Project | Mahmoud | Subhash | No | Availability Managment : To fitch the common filed from estimrar automatically Capacity Management: Integration between the Estimrar list SharePoint and the Capacity Plan SharePoint, enabling users to select the service name when initiating the capacity plan, after selection, all common fields are automatically fetched from Estimrar list into the capacity plan. |  | TBD | Automation | Vibe coding | Inprogress | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
TP-Site Managerial Audit Agent |  |  | Project | Jamil | Alexandre | No | he Transmission Site Audit & Inspection App enables site engineers to conduct and record audits digitally from the field, capturing real-time data, photos, and observations, while ensuring automated notifications and efficient tracking of inspection findings to closure. |  | TBD | Automation | Vibe coding | Inprogress | Development | Pre ISRP | 0.35 | TP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
DEWA Stakeholders Engagement Platform |  |  | Project | Jamil | NA | Yes | A unified platform for end-to-end DEWA stakeholder engagement, enabling event management, communication, feedback, and analytics at enterprise scale. |  | TBD | Automation | Power Platform | Inprogress | Initiation | Requierment Gathering | 0.02 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
HSE Reporting Platform |  |  | Project | Jamil | Sumathi M | No | HSE incident, Near-Miss & Safety Observation Platform | 2026-02-05 00:00:00 | TBD | Vibe Coding | Vibe Coding | Inprogress | Development | Pre ISRP | 0.6 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Log Framework Dashboard |  |  | Project | Jamil | Sumathi M | No | Centralised Dashboard for the Automation Logs done by the Bots | 2026-02-05 00:00:00 | TBD | Vibe Coding | Vibe Coding | Inprogress | Development | Pre ISRP | 0.85 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Universal Service Centre | DR21-0275 |  | Project | Jamil | Sumathi M | No | Processing & tracking inquiry and video chat service requests in universal service centre | 2026-02-05 00:00:00 | TBD | Automation | Vibe Coding | Inprogress | Development | Pre ISRP | 0.2 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Procure-to-ID Outsource Tracking Portal | - | Adhoc | Project | Jamil | Anjana Sukumaran | No | A portal that tracks outsourced procurement and Moro partner ID creation requests from approved MEMO through PO to completed ID issuance. | 2026-02-05 00:00:00 | TBD | Automation | Vibe Coding | Inprogress | Development | Requierment Gathering | 0.15 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
ATQEN | DR25_000231 | Kofax Migration | Project | Priyanka | Anjana | No | ATQAN process for internal users, enabling structured multi-stage case management, review, and approval workflows across INOC and TS&C process types | 20/4/2026 | TBD | Automation | Power Platform | Inprogress | Initiation | Requierment Gathering | 0.03 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
DEWA Vulnerability Monitor |  |  | Project | Jamil | Mohammad Sajid Rajnagarwala | No | Real-time CVE/Vulnerability tracking system |  | TBD | Automation | Vibe Coding | Inprogress | Development | Pre ISRP | 0.15 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Vendor Leave Tracker Agent | TBD | Adhoc | Project | Jamil | Akash Rankhamb | No | Leave Tracker for Vendors Resources Employees and to track the productivity for the resosurces. | 17/04/2026 | TBD | AI Agent | Vibe Coding | Inprogress | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
DEWA-Software Lifecycle |  |  | Project | Jamil | Sumit/Subhash | No | Centralized management tool to track all the record of the project in one platform,integrated with for real time Azure Board details. |  | TBD | Automation | Vibe Coding | Inprogress | Initiation | Requierment Gathering | 0 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
AI OS |  |  | Project | Ricardo | Alexandre |  | Dev of DEWA App inside Chat GPT |  |  | AI | Custom Code | Inprogress | Development | Pre ISRP | 0.85 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Document AI Support for e-Invoicing KYC Verification |  |  | Project | Mahmoud | Sofia | No | DEWA needs to ensure that the KYC details of customers in the company category are accurate. The required data includes trade license details, company name, address (street, building, emirate), VAT number, and TIN (Tax Identification Number). |  | 2026-06-30 00:00:00 | AI Automation | Power Platform | Inprogress | Initiation | Requierment Gathering | 0.1 | Billing |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Health & Safety Agent |  |  | Project | Jamil | Alexandre | No | Agent to respond to questions about health and safety |  | TBD | AI Agent | Copilot Studio | Inprogress | UAT | Post ISRP | 0.9 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Harmonics | DR25_000231 | Kofax Migration | Project | Priyanka | Prem | No | The Harmonics service enables Shams Dubai solar applicants to self-check their rooftop PV inverter design against DEWA Power Quality limits before submitting a Design Approval application. The service replaces the legacy KOFAX TotalAgility web form and automates harmonic factor assessment, PDF report generation, and SAP CRM data submission | 2026-05-20 00:00:00 | 2026-08-17 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.15 | EVP Office |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
SmartBidder | DR25_000231 | Kofax Migration | Project | Priyanka | Sumathi M | No | fkari | 21/05/2026 | 2026-08-17 00:00:00 | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.15 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
ASAS | DR25_000231 | Kofax Migration | Project | Jamil | Priyanka | No |  | 2026-06-11 00:00:00 | 2026-10-16 00:00:00 | Automation | Power Platform + Vibe coding | Pipeline | Initiation | Requierment Gathering | 0.02 | P&WP |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Audit AI UseCase |  |  |  | Mahmoud | Ricardo |  |  |  |  | Automation |  | Inprogress | Initiation | Requierment Gathering | 0.02 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
E-Invoicing Customer Profile Updating |  |  |  | Mahmoud | Sofia |  |  |  |  | Automation |  | Inprogress | Development | Pre ISRP | 0.15 |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Collection Online transaction system | DR25_000231 | Kofax Migration | Project | Priyanka | Akash Rankhamb | No |  | 2026-01-06 00:00:00 | TBD | Automation | Vibe Coding | Inprogress | Initiation | Requierment Gathering | 0.1 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Smart Media Dashboard | DR25_000231 | Kofax Migration | Project | Priyanka | Akash Rankhamb | No |  | 2026-12-06 00:00:00 | TBD | Automation | Vibe Coding | Inprogress | Initiation | Requierment Gathering | 0.1 | S&GC |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Do Daily Report | DR25_000231 | Kofax Migration |  | Priyanka | Rakul |  |  | 2026-06-22 00:00:00 |  | Automation |  |  | Initiation | Requirement Gahering | 0.02 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
WCA Enhancement | DR25_000231 | Kofax Migration |  | Priyanka | Anjana Sukumaran |  |  | 2026-02-17 00:00:00 |  | Automation | Power Platform | Inprogress | Development | Pre ISRP | 0.65 |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
AlHasba Air passage |  |  |  | Mahmoud | [5 empty] | AlHasbah |  | Inprogress | Initiation | Requirement Gahering | 0.02 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
AlHasba Chatbot ph1 |  |  |  | Mahmoud | [5 empty] | AlHasbah |  | Inprogress | Initiation | Requirement Gahering | 0.02 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
AlHasba Bonus |  |  |  | Mahmoud | [5 empty] | AlHasbah |  | Inprogress | Initiation | Requirement Gahering | 0.02 | BS&HR |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
PO-Based Payment Processing | AIFC26-68-AIFC26-67-AIFC26-69-AIFC26-82 | PO-Based Payment Processing | Alhasbah | Rami | Saeed/Abdul rasheeque | No |  | TBD | TBD | AlHasbah | n8n | Inprogress | Initiation | Requirement Gahering | 0.02 | Finance |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
FIN-Daily Bank Reconciliation | DR25_000231 | Kofax Migration | Project | Priyanka | Sumathi M | No |  | TBD | TBD | Automation | Power Platform | Pipeline | Initiation | Requirement Gahering | 0 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Customer Complaints System Notification | DR25_000231 | Kofax Migration | Project | Priyanka | Sumathi M | No | Resident Engineers working under Intelligent & response department monitors the DEWA IT Devices & Services by True Sight 24/7 Application and reports to concerned engineering team for action if any outages/anomalies are observed. | TBD | TBD | Automation | Power Platform | Pipeline | Initiation | Requirement Gahering | 0 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Fin-Lineloss | DR25_000231 | Kofax Migration | Project | Priyanka | Sumathi M | No | This process outlines the end-to-end workflow for collecting, consolidating, and reporting divisional data submitted monthly by employees across the TP, DP, and Generation divisions to the Finance team. | 21/05/2026 |  |  |  | Pipeline | Initiation | Requirement Gahering | 0 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
PO Related Payment Agent | - | n8n | Project | Saeed | abdul rasheeque |  | This process uses an AI agent to extract and classify SAP invoice data into four categories—Local Purchase, Contract Purchase, Staff Payments, and Direct Non-PO—then automatically applies the relevant validation and approval workflows. | 24/06/2026 | oct-2026 As Per PMD | AlHasbah | n8n | Inprogress | Initiation | Requirement Gahering | 0.02 | Finance |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Capacity Plan | DR26-396 | Adhoc | Project | Mahmoud | Sumit Kumar | No | Portal to track on the server capacity across department | 2026-04-05 00:00:00 | TBD | Automation | Vibe Coding | Inprogress | Development | Requierment Gathering, SDD, Development | 0.3 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Catering Service | DR24-0257 | Adhoc | Project | Mahmoud | Sumit Kumar | No | Centrlaized hub to track all the catering request across departments & locations | 2026-01-05 00:00:00 | 30/06/2026 | Automation | Vibe Coding | Completed | Pre-Production | Post ISRP | 0.85 | I&TF |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Datahub | DR26-169 | Adhoc | Project | Mahmoud | Sumit Kumar | No | Centrlaized hub to track all External requests , attributes and Datasets across the Data governance team. | 2026-02-25 00:00:00 | 30/06/2026 | Automation | Vibe Coding | Completed | Pre-Production | Post ISRP | 0.85 | I&TF
(untitled) | DR25_000231
Facility management portal | DR24-0230 | Adhoc | Project | Mahmoud | Subhash chavan | No | pahse 1 admin master details and facility soft services including car wash,cleaning,general and waste,paper and pastic,pest and rodent | 2026-01-05 00:00:00 | 30/06/2026 | Vibe Coding | Power platform | completed | pre-production | Post ISRP | 0.85 | I&TF
Refreshment portal |  | Adhoc | Project | Project | Subhash chavan | No |  | 2026-02-25 00:00:00 | 30/06/2026 | Vibe Coding | Power platform | completed | pre-production | Post ISRP | 0.85 | I&TF
EVP Returned Memo Report |  |  | Project | Mahmoud | Priyanka/ Anjana | No | Cancelled |  | On Hold |  | Power Platform | Cancelled | Cancelled |  | 0.7 | I&TF | [13 empty] | (similar system exists)
Parking Pass Automation |  |  | Project | Mahmoud | Sumit/Subhash | No | Transferred TO SAP |  |  |  | Power Platform | Cancelled | Cancelled |  | 0.05 | BS&HR | [13 empty] | To be Cancelled through PP
Project Manager Agent |  |  | Initiative Internal | Ricardo | Ricardo | No | - |  | Cancelled |  | Copilot Studio | Cancelled | Cancelled |  | 0.7 | I&TF
Survey Certificate Generation |  |  | Initiative Internal | Ricardo | Ricardo | No | - |  | Completed |  | Power Platform | Cancelled | Cancelled |  | 1 | I&TF
AI Excellence |  |  | Initiative Internal | Ricardo | Sofia | No | - |  | TBD |  | Copilot Studio + Vibe Coding | Cancelled | Cancelled |  | 0.05 | I&TF