## import
Use Case Name | Use Case ID | Description | Division | Domain | SAP Module | Status | Agent ID | Start Date | Planned Go Live | Actual Go Live | Target End Date | Systems For Integration | Measurement Type | Annual Volume | Expected Efficiency | FTE Avoidance | Current State | Future State | Total Development Effort | Processes | Target Cost Saving | FTE Savings Target
SUPPLY MANAGEMENT REVAMP: MOVE-IN - PHASE 1 | uc-001-supply-management-revamp-move-in-phase-1 | CUSTOMER MOVE-IN | Billing | CUSTOMER 360 | SAP | live | agent-001-account-validator | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 0 | 20 | 0 |  |  |  | null
TENDER BOND - VERIFICATION | uc-002-tender-bond-verification | CONTRACTS MANAGEMENT | Billing | CUSTOMER 360 | SAP | pipeline | agent-001-account-validator | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 3000 | 0 | 0 |  |  |  | null
​AUTO-CLEARING OF GL & SUB-ACCOUNTS | uc-003-auto-clearing-of-gl-sub-accounts | E&W CONNECTIONS | Billing | CUSTOMER 360 | SAP | live | agent-001-account-validator | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 12000 | 0 | 0 |  |  |  | null
NON BP - ​APPROVAL OF FREE-OF-COST ITEMS | uc-004-non-bp-approval-of-free-of-cost-items | JOB COSTING | Billing | CUSTOMER 360 | SAP | planned | agent-001-account-validator | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] | Transactions | 260 | 0 | 0 |  |  |  | null
NON BP - ​AUTO-ACCOUNTING CLEARING OF DAMAGE CLAIMS | uc-005-non-bp-auto-accounting-clearing-of-damage-claims | E&W CONNECTIONS | Billing | CUSTOMER 360 | SAP | planned | agent-001-account-validator | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] | Transactions | 10000 | 0 | 0 |  |  |  | null
NON BP - VENDOR CREDIT NOTE POSTING & ADJUSTMENTS | uc-006-non-bp-vendor-credit-note-posting-adjustments | CONTRACTS MANAGEMENT | Billing | CUSTOMER 360 | SAP | pipeline | agent-001-account-validator | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 180 | 0 | 0 |  |  |  | null
SECURITY DEPOSIT REFUND AUTOMATION <=AED 4000 | uc-007-security-deposit-refund-automation-aed-4000 | DEPOSIT REFUNDS | Billing | CUSTOMER 360 | SAP | live | agent-002-account-validator-and-consolidation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 0 | 100 | 1.6 |  |  |  | null
ACCOUNT VALIDATOR | uc-008-account-validator | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-002-account-validator-and-consolidation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 10 |  |  |  | null
EXTERNAL TRAINING PROGRAMS- SAP LEARNING SOLUTIONS | uc-009-external-training-programs-sap-learning-solutions | EXTERNAL TRAINING PROGAM ATTANDANCE AND CERTIFCATE GENERATION | HR | LEARNING & DEVELOPMENT | SAP | pipeline | agent-003-agentic | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "POWER AUTOMATE"] |  | 35000 | 100 | 0 |  |  |  | null
LEASED ACCOMMODATION | uc-010-leased-accommodation | BENEFITS & CLAIMS | HR | C&B-EH, PERSONNEL MANAGEMENT | SAP | planned | agent-004-allowance-verification-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS", "APIGEE"] | Requests | 1500 | 100 | 1.3 |  |  |  | null
MOBILE ALLOWANCE AUTOMATION | uc-011-mobile-allowance-automation | MOBILE ALLOWANCE | HR | C&B-EH, PERSONNEL MANAGEMENT | SAP | planned | agent-004-allowance-verification-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] | Requests | 1000 | 99 | 0.1 |  |  |  | null
PERMISISON FOR CONTINUING EDUCATION | uc-012-permisison-for-continuing-education | TALENT MANAGEMENT | HR | C&B-EH, PERSONNEL MANAGEMENT | SAP | planned | agent-004-allowance-verification-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] | Requests | 150 | 90 | 0.01 |  |  |  | null
CHILDREN EDUCATION FEES | uc-013-children-education-fees | BENEFITS & CLAIMS | HR | C&B-EH, PERSONNEL MANAGEMENT | SAP | planned | agent-004-allowance-verification-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] | Transactions | 2000 | 90 | 0.33 |  |  |  | null
ANOMALY DETECTION AND READING PREDICTION | uc-014-anomaly-detection-and-reading-prediction | BILLING | Billing | PREDICTIVE METER, ANOMALY DETECTION AND READING | SAP | planned | agent-005-anomaly-detection-and-reading-prediction | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
AUTOMATICALLY CALCULATES AND UPDATES HOUSING FEES FOR OWNERS AND TENANTS | uc-015-automatically-calculates-and-updates-housing-fees-for-owners | BILLING | Billing | CUSTOMER 360 | SAP | pipeline | agent-006-automate-housing-fees-update-during-owner-and-tenant-move-in | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 80 | 0 |  |  |  | null
OWNER MOVE-IN / OUT | uc-016-owner-move-in-out | BILLING | Billing | CUSTOMER 360 | SAP | pipeline | agent-007-automate-owner-move-in-process | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 34500 | 0 | 0 |  |  |  | null
REDUCED CALL CENTER DEPENDENCY ( MOVE-IN /MOVE-OUT /CONSUMPTION VERIFICATION ) | uc-017-reduced-call-center-dependency-move-in-move-out-consumption- | BILLING | Billing | CUSTOMER 360 | SAP | pipeline | agent-008-automated-sms-and-email-notifications-keep-customers-informe | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 108941 | 80 | 0 |  |  |  | null
AUTO ACTIVATION OF UN-AUTHORIZATION METER ACTIVATION | uc-018-auto-activation-of-un-authorization-meter-activation | DISCONNECTION AND RECONNECTION OF SUPPLY | Billing | CUSTOMER 360 | SAP | live | agent-009-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
AUTOMATE EJARI PROCESS FOR CONSULATE CUSTOMERS (ORGANIZATION) | uc-019-automate-ejari-process-for-consulate-customers-organization | AUTOMATE EJARI PROCESS FOR CONSULATE CUSTOMERS (ORGANIZATION) — automation use case managed by AUTOMATION. | Billing | CUSTOMER 360 | SAP | pipeline | agent-009-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
PROACTIVE INITIATION OF NEW CONNECTION PROCESS FOR COMMERCIAL MOVE-IN (METER NOT INSTALLED) CASES | uc-020-proactive-initiation-of-new-connection-process-for-commercia | PROACTIVE INITIATION OF NEW CONNECTION PROCESS FOR COMMERCIAL MOVE-IN (METER NOT INSTALLED) CASES — automation use case managed by AUTOMATION. | Billing | CUSTOMER 360 | SAP | pipeline | agent-009-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
AUTOMATIC RECONNECTION ORDER CREATION | uc-021-automatic-reconnection-order-creation | RECONNECTION ORDER GENERATION | Billing | CUSTOMER 360 | SAP | live | agent-009-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 88000 | 0 | 0 |  |  |  | null
AUTOMATED CUSTOMER NOTIFICATIONS | uc-022-automated-customer-notifications | DISCONNECTION AND RECONNECTION OF SUPPLY | Billing | CUSTOMER 360 | SAP | live | agent-009-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 90000 | 75 | 0 |  |  |  | null
DET–DUL integration in Move In | uc-023-detdul-integration-in-move-in | DET–DUL integration in Move In — automation use case managed by Automation. | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
Customer Profile Revamp | uc-024-customer-profile-revamp | Customer Profile Revamp | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "WEBSITE", "APIGEE"] |  | 0 | 0 | 0 |  |  |  | null
Unified Tracking - Phase1 | uc-025-unified-tracking-phase1 | Unified Tracking | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["WEBSITE", "APIGEE", "SAP"] |  | 0 | 0 | 0 |  |  |  | null
Unified Password Policy | uc-026-unified-password-policy | Unified Password Policy — automation use case managed by Automation. | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "APIGEE", "WEBSITE"] |  | 0 | 0 | 0 |  |  |  | null
DM Violation Revamp | uc-027-dm-violation-revamp | DM Violation Revamp | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
Rate Category Mismatch | uc-028-rate-category-mismatch | Rate Category Mismatch — automation use case managed by Automation. | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | planned | agent-010-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
EV Registration enhancement | uc-029-ev-registration-enhancement | EV Registration enhancement | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | live | agent-010-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
ERMS Process for KAM Customers | uc-030-erms-process-for-kam-customers | ERMS Process for KAM Customers | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
04 System integration | uc-031-04-system-integration | 04 System integration | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
RERA proactive actions | uc-032-rera-proactive-actions | RERA proactive actions | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | planned | agent-010-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
EV Enhancement - Sprint 1 | uc-033-ev-enhancement-sprint-1 | EV Enhancements | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
EV Consumption graph for CCC | uc-034-ev-consumption-graph-for-ccc | EV Consumption graph | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | live | agent-010-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
Refund Status and Marketing subscription | uc-035-refund-status-and-marketing-subscription | Refund Status and Marketing subscription | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
Move-In Reconnection order automation – Existing Owners | uc-036-move-in-reconnection-order-automation-existing-owners | Owner Move-In | Innovation | CUSTOMER 360, Cross-Layer Automation | SAP | pipeline | agent-010-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
DAILY COLLECTION RECONCILLIATION & MONTHLY BANK RECONCILLIIATION | uc-037-daily-collection-reconcilliation-monthly-bank-reconcilliiati | AUTOMATE DAILY COLLECTION AND MONTHLY BANK RECONCILIATION PROCESSES TO REDUCE MANUAL WORKLOAD AND IMPROVE ACCURACY AND SPEED. | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-011-bank-control-reconcilliation-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
BANK GUARANTEES | uc-038-bank-guarantees | STREAMLINE AND CONTROL THE END-TO-END BANK GUARANTEE LIFECYCLE TO REDUCE INVALID/EXPIRED COVERAGE & MANUAL TRACKING. | Finance | CONTRACTS FACILITATION | SAP | planned | agent-012-bank-guarantees-lifecycle-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
BILLING VALIDATION AND RECONCILIATION | uc-039-billing-validation-and-reconciliation | BILLING | Billing | PRO-ACTIVE RISK SEGMENTATION | SAP | planned | agent-013-billing-validation-and-reconciliation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
​RECONCILIATION OF SUBSIDIARY DATA IN GR | uc-040-reconciliation-of-subsidiary-data-in-gr | FINANCIAL ACCOUNTING & CORPORATE TAX | Billing | PRO-ACTIVE RISK SEGMENTATION | SAP | pipeline | agent-013-billing-validation-and-reconciliation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "Rammas"] |  | 2 | 0 | 0 |  |  |  | null
CASE DOCUMENTATION AI | uc-041-case-documentation-ai | AI DRAFTS, VALIDATES, AND ARCHIVES CASE-RELATED DOCUMENTS AND SUMMARIES IN STANDARDIZED FORMAT | HR | TALENT MANAGEMENT | SAP | planned | agent-014-career-case-management-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 20000 | 90 | 1 |  |  |  | null
COMPENSATION STRATEGY | uc-042-compensation-strategy | BENCHMARKING INTERNAL AND EXTERNAL COMPENSATION AND COMPENSATION PLANNING | HR | C&B-EH | SAP | planned | agent-015-compensation-strategy-planning-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 2 | 90 | 0.02 |  |  |  | null
CONTRACT INSURANCE | uc-043-contract-insurance | CONTRACTS MANAGEMENT | Finance | CONTRACTS FACILITATION | SAP | pipeline | agent-016-contract-insurance-management-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
SUPPLIER FINANCIAL CAPABILITY REVIEW USING AI | uc-044-supplier-financial-capability-review-using-ai | CONTRACTS MANAGEMENT | Finance | CONTRACTS FACILITATION | SAP | pipeline | agent-017-contract-placement-evaluation-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
CONTRACT PAYMENTS | uc-045-contract-payments | STREAMLINE VENDOR PAYMENT READINESS TO REDUCE MANUAL EFFORT AND PROCESSING TIME. | Finance | CONTRACTS FACILITATION | SAP | planned | agent-018-contract-settlements-support-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
CUSTOM DUTY EXEMPTIONS | uc-046-custom-duty-exemptions | AUTOMATE AND CONTROL THE END-TO-END CUSTOMS DUTY EXEMPTION APPLICATION LIFECYCLE TO ELIMINATE MANUAL HANDLING AND IMPROVE CYCLE TIME | Finance | CONTRACTS FACILITATION | SAP | live | agent-019-custom-duty-exemption-orchestration-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
UNIFIED TRACKING | uc-047-unified-tracking | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-020-customer-tracking-service | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "WEBSITE"] |  | 0 | 80 | 0 |  |  |  | null
DATA VALIDATOR | uc-048-data-validator | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-021-data-validator | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 5 |  |  |  | null
AUTOMATE END-TO-END DEBIT ADVICE (DA) PREPARATION AND CONTROL FOR CHARGEABLE CONNECTION JOBS TO REDUCE CYCLE TIME, MANUAL VALIDATION, AND REWORK). | uc-049-automate-end-to-end-debit-advice-da-preparation-and-control- | AUTOMATE END-TO-END DEBIT ADVICE (DA) PREPARATION AND CONTROL FOR CHARGEABLE CONNECTION JOBS TO REDUCE CYCLE TIME, MANUAL VALIDATION, AND REWORK. | Finance | SMART PROJECT & COSTING FINANCE | SAP | planned | agent-022-debit-advice-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
ELIGIBILITY & CASE INTELLIGENCE (ACTIONS) | uc-050-eligibility-case-intelligence-actions | AI EVALUATES EMPLOYEE ELIGIBILITY FOR BENEFITS OR CASES USING POLICY AND HISTORICAL DATA LOGIC | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-023-eligibility-performance-decisioning-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 10000 | 90 | 0 |  |  |  | null
BONUS | uc-051-bonus | BONUS AUTOMATION | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-024-employee-benefits-claims-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 10000 | 0 | 0.04 |  |  |  | null
AIR PASSAGE APPLICATION | uc-052-air-passage-application | BENEFITS & CLAIMS | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-024-employee-benefits-claims-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] | Transactions | 9000 | 99 | 0.74 |  |  |  | null
FULL DMS SYSTEM | uc-053-full-dms-system | FULL DMS SYSTEM — automation use case managed by EMPLOYEE FILE AGENT. | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-025-employee-file-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "NEPTUNE", "SMARTOFFICE"] |  | 0 | 0 | 0 |  |  |  | null
INTELLIGENT TICKET CLASSIFICATION & ROUTING | uc-054-intelligent-ticket-classification-routing | AI CLASSIFIES SERVICE REQUESTS AND ROUTES THEM AUTOMATICALLY TO THE CORRECT HR OR IT QUEUE | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-026-employee-hr-self-service-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] | Requests | 2000 | 60 | 0.02 |  |  |  | null
EMPLOYEE SELF-SERVICE AI ASSISTANT-POLICY & PROCEDURE | uc-055-employee-self-service-ai-assistant-policy-procedure | CONVERSATIONAL AI ASSISTS EMPLOYEES WITH HR QUERIES, REQUESTS, AND STATUS TRACKING IN REAL TIME | HR | PERSONNEL MANAGEMENT | NEPTUNE | pipeline | agent-026-employee-hr-self-service-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["NEPTUNE"] | Transactions | 100000 | 90 | 0.95 |  |  |  | null
EMPLOYEE SELF-SERVICE AI ASSISTANT- CONVERSATIONAL | uc-056-employee-self-service-ai-assistant-conversational | CONVERSATIONAL AI ASSISTS EMPLOYEES WITH HR QUERIES, REQUESTS, AND STATUS TRACKING IN REAL TIME | HR | PERSONNEL MANAGEMENT | NEPTUNE | planned | agent-026-employee-hr-self-service-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["NEPTUNE"] | Transactions | 100000 | 90 | 0.95 |  |  |  | null
RESIGNATION/NO DUE CLEARANCE & FINAL SETTLEMENT | uc-057-resignationno-due-clearance-final-settlement | PERSONNEL ADMINISTRATION | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-027-employee-lifecycle-exit-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] | Requests | 300 | 0 | 0.66 |  |  |  | null
Personal ID | uc-058-personal-id | EMIRATES ID / PASSPORT UPDATE | HR | PERSONNEL MANAGEMENT | SAP | live | agent-028-employee-residency-identity-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP", "RAMMAS"] | Requests | 1482 | 90 | 0.13 |  |  |  | null
Family Members | uc-059-family-members | UPDATE FAMILY MEMBERS RECORDS | HR | PERSONNEL MANAGEMENT | SAP | live | agent-028-employee-residency-identity-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP", "RAMMAS"] | Transactions | 4200 | 90 | 0.06 |  |  |  | null
FAMILY VISA REIMBURSEMENT | uc-060-family-visa-reimbursement | AUTO PAYMENT OF REIMBURSEMENT | HR | PERSONNEL MANAGEMENT | SAP | live | agent-028-employee-residency-identity-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP", "RAMMAS"] | Transactions | 2398 | 70 | 1.06 |  |  |  | null
BUSINESS VISA REIMBURSEMENT | uc-061-business-visa-reimbursement | MERGING BUISNESS VISA REIMBURSEMENT WITH TRAVEL EXPENSE CLAIM | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-029-employee-residency-and-identity-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "RAMMAS"] | Transactions | 400 | 70 | 0.04 |  |  |  | null
TRAVEL EXPENSE SUBMISSION | uc-062-travel-expense-submission | INTRODUCE AI BASED OCR FOR TRAVEL EXPENSE | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-029-employee-residency-and-identity-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "RAMMAS"] | Transactions | 2000 | 90 | 0.03 |  |  |  | null
SICK LEAVE AUTOMATION | uc-063-sick-leave-automation | LEAVE REQUEST | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-030-employee-time-management-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "RAMMAS", "APIGEE"] | Requests | 32209 | 90 | 0.46 |  |  |  | null
RPA FOR FIXING MISSING PUNCHES | uc-064-rpa-for-fixing-missing-punches | TO CLEAN MISSING OR MULTIPLE PUNCH RECORDS TO AVOID TIME EVALUATION ERRORS | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-030-employee-time-management-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "POWER AUTOMATE"] |  | 12000 | 100 | 0 |  |  |  | null
RPA FOR FIXING OVERLAPPING TIME RECORDS | uc-065-rpa-for-fixing-overlapping-time-records | TO CLEAN OVERLAPPING RECORDS WHERE THERE IS LEAVE RECORD AND PUNCH IN AND OUT RECORDS TO AVOID TIME EVALUATION ERRORS | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-030-employee-time-management-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "POWER AUTOMATE"] |  | 10000 | 100 | 0 |  |  |  | null
TEJORI AL SAADA | uc-066-tejori-al-saada | EMPLOYEE REWARD PROCESS | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-030-employee-time-management-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 24023 | 0 | 0.08 |  |  |  | null
PARTICIPATE IN SPORTS EVENT | uc-067-participate-in-sports-event | IMPLEMENT SPORTS EVENT SYSTEM | HR | C&B-EH | SAP | planned | agent-031-employee-well-being-engagement-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 50 | 100 | 0.21 |  |  |  | null
EX-EMPLOYEE SERVICES | uc-068-ex-employee-services | EX-EMPLOYEE SERVICES — automation use case managed by EX-EMPLOYEE SERVICES AGENT. | HR | PERSONNEL MANAGEMENT | AI ENGINEERING | planned | agent-032-ex-employee-services-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
EXPLAINABLE BILLING AGENT | uc-069-explainable-billing-agent | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-033-explainable-billing-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
BUDGET SUPPORT AGENT | uc-070-budget-support-agent | AUTOMATE AND STANDARDIZE THE DEVELOPMENT, REFRESH, AND GOVERNANCE OF THE FINANCE STRATEGY (MULTI-YEAR & ANNUAL PRIORITIES) BY REDUCING MANUAL DATA GATHERING AND REPORT-GENERATION AND IMPROVED ANALYTIC | Finance | INTELLIGENT REPORTING & STRATEGIC FINANCE | SAP | planned | agent-034-finance-strategy-performance-management-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
GENERAL ASSET INSURANCE REQUESTS (ADDITION,RENEWAL, DELETION) | uc-071-general-asset-insurance-requests-additionrenewal-deletion | AUTOMATE THE GENERAL INSURANCE ASSET LIFECYCLE (ADDITION, DELETION, AND RENEWALS). | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-035-general-asset-insurance-administration-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
GENERAL ASSET CLAIMS | uc-072-general-asset-claims | REDUCE TIME-TO-SETTLEMENT IN ASSET CLAIMS BY STANDARDIZING INCIDENT-TO-CLAIM WORKFLOWS. PROPOSED SOLUTION: | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-036-general-insurance-asset-claims-management-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
MAJOR ASSET VALUATION | uc-073-major-asset-valuation | AUTOMATE AND STREAMLINE THE MAJOR ASSET VALUATION CYCLE PROCESS TO REDUCE REVIEW EFFORT AND REWORK | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-037-general-insurance-asset-valuation-support-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 45000 | 0 | 0 |  |  |  | null
GENERAL INSURANCE TENDERING | uc-074-general-insurance-tendering | ACCELERATE AND STANDARDIZE GENERAL INSURANCE TENDER PREPARATION AND EVALUATION TO REDUCE MANUAL HANDLING OF DATA AND REPORTING | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-038-general-insurance-tenders-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 1 | 0 | 0 |  |  |  | null
BATCH SAP UPDATE AUTOMATION | uc-075-batch-sap-update-automation | AUTOMATED BULK DATA UPDATES IN SAP WITH VALIDATION CHECKS AND EXCEPTION HANDLING THROUGH AI | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-039-hr-payroll-operations-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 185898 | 90 | 1 |  |  |  | null
IDENTITY CONFORMATION | uc-076-identity-conformation | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-040-identity-conformation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
JD CREATION & MANAGEMENT AGENT | uc-077-jd-creation-management-agent | AI DRAFTS, STANDARDIZES, AND UPDATES JOB DESCRIPTIONS ALIGNED WITH DEWA’S COMPETENCY FRAMEWORK | HR | PERSONNEL MANAGEMENT | SAP | pipeline | agent-041-job-architecture-evaluation-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "RAMMAS"] |  | 6495 | 100 | 2.49 |  |  |  | null
BALANCE SCORECARD REPORT ALONG WITH KPI WORKFLOW | uc-078-balance-scorecard-report-along-with-kpi-workflow | FINANCE STRATEGY & PERFORMANCE MANAGEMENT | Finance | INTELLIGENT REPORTING & STRATEGIC FINANCE | SAP | live | agent-042-kpi-workflow-orchestration-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
L&D REPORTING & KPI CONSOLIDATION | uc-079-ld-reporting-kpi-consolidation | L&D REPORTING & KPI CONSOLIDATION — automation use case managed by L&D REPORTING & KPI CONSOLIDATION AGENT. | HR | LEARNING & DEVELOPMENT | SAP | planned | agent-043-ld-reporting-kpi-consolidation-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["NEPTUNE", "SAP"] |  | 0 | 0 | 0.8 |  |  |  | null
LIQUIDATED DAMAGES | uc-080-liquidated-damages | STANDARDIZE AND SPEED UP LIQUIDATED DAMAGES COMPUTATION AND RECOVERY, REDUCING LEAKAGE AND ENSURING CONTRACTUAL COMPLIANCE | Finance | CONTRACTS FACILITATION | SAP | planned | agent-044-liquidated-damages-recovery-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
SUPPLIER INVOICE VERIFICATION USING AI | uc-081-supplier-invoice-verification-using-ai | SUPPLIER INVOICE | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | live | agent-045-local-purchase-orders-lpo-payments-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP", "SAP PI/PO", "RAMMAS"] |  | 54000 | 0 | 0 |  |  |  | null
MASS APPROVAL LEAVE | uc-082-mass-approval-leave | MASS APPROVAL OF LEAVES | HR | PERSONNEL MANAGEMENT | SAP | live | agent-046-manager-time-management-agent | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 200000 | 100 | 0.2 |  |  |  | null
TIME DATA AUDITING | uc-083-time-data-auditing | TIME DATA AUDITING — automation use case managed by MANAGER TIME MANAGEMENT AGENT. | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-046-manager-time-management-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "NEPTUNE", "SMARTOFFICE", "RAMMAS"] |  | 0 | 0 | 0.21 |  |  |  | null
MEDICAL INSURANCE APPLICATIONS (ADDITION,RENEWAL, CANCELATIONS) | uc-084-medical-insurance-applications-additionrenewal-cancelations | AUTOMATE AND CONTROL STAFF MEDICAL INSURANCE MEMBERSHIP LIFECYCLE CHANGES TO REDUCE MANUAL WORKLOAD. | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-047-medical-insurance-administration-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
MEDICAL INSURANCE REIMBURSEMENT CLAIMS | uc-085-medical-insurance-reimbursement-claims | STREAMLINE AND STANDARDIZE REIMBURSEMENT CLAIMS (MEDICAL & WORK ACCIDENT | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-048-medical-insurance-claims-processing-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
MEDICAL INSURANCE TENDERING | uc-086-medical-insurance-tendering | STREAMLINE AND STANDARDIZE THE MEDICAL INSURANCE TENDERING PROCESS | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-049-medical-insurance-tender-support-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 1 | 0 | 0 |  |  |  | null
METER HEALTH AGENT | uc-087-meter-health-agent | BILLING | Billing | PREDICTIVE METER, ANOMALY DETECTION AND READING | SAP | planned | agent-050-meter-health-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
UTILITY AGENT FOR BILLING USER | uc-088-utility-agent-for-billing-user | BILLING | Billing | PREDICTIVE METER, ANOMALY DETECTION AND READING | SAP | planned | agent-051-meter-reading | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
MIS REPORTING | uc-089-mis-reporting | AUTOMATE AND STANDARDIZE MIS REPORTING CYCLE TO REDUCE MANUAL CONSOLIDATION AND REWORK, IMPROVE CONSISTENCY, AND INCREASE QUALITY OF PERFORMANCE INSIGHTS | Finance | INTELLIGENT REPORTING & STRATEGIC FINANCE | SAP | planned | agent-052-mis-reporting-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
NON-PO DIRECT PAYMENTS | uc-090-non-po-direct-payments | REDUCE PROCESSING TIME AND MANUAL HANDLING FOR NON-PO DIRECT PAYMENTS | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-053-non-po-direct-payment-operations-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
NOTICE OF INJURY | uc-091-notice-of-injury | NOTICE OF INJURY — automation use case managed by NOTICE OF INJURY AGENT. | HR | PERSONNEL MANAGEMENT | NEPTUNE | planned | agent-054-notice-of-injury-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["NEPTUNE"] |  | 0 | 0 | 0.9 |  |  |  | null
OUTREACH AUTOMATION | uc-092-outreach-automation | BILLING | Billing | PRO-ACTIVE RISK SEGMENTATION | SAP | planned | agent-055-outreach-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
PAYROLL CONTROL CENTER | uc-093-payroll-control-center | PAYROLL | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-056-payroll-control-center-pcc | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 100 | 80 | 4 |  |  |  | null
UPDATE OFFCYCLE PAYROLL ENTRIES | uc-094-update-offcycle-payroll-entries | UPDATE AWARDS, LUNCH ALLOWANCE, TELEPHONE EXPENSES ETC. FROM MEMO TO SAP OFFCYLE INFOTYPE USING AI OCR FUNCTIONALITIES | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | live | agent-056-payroll-control-center-pcc | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] |  | 10000 | 95 | 1 |  |  |  | null
RETIREMENT/RETIREMENT EXTENSION | uc-095-retirementretirement-extension | PERSONNEL ADMINISTRATION | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-057-personnel-affairs-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] | Requests | 400 | 0 | 0.04 |  |  |  | null
TRANSPORTATION OF PERSONAL BELONGINGS | uc-096-transportation-of-personal-belongings | PROCESS TO BE IMPLEMENTED TO ARRANGE FOR TRANSPORTATION OF PERSONAL BELONGINGS | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-057-personnel-affairs-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 100 | 90 | 0.01 |  |  |  | null
CONFLICT OF INTEREST | uc-097-conflict-of-interest | INTRODUCE AI IN CONFLICT OF INTEREST PROCESS | HR | PERSONNEL MANAGEMENT | SAP | planned | agent-057-personnel-affairs-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 230 | 90 | 0 |  |  |  | null
JOB COSTING | uc-098-job-costing | AUTOMATE AND STREAMLINE END-TO-END PROJECT JOB COSTING CYCLE TO IMPROVE SPEED, CONSISTENCY, AND GOVERNANCE | Finance | SMART PROJECT & COSTING FINANCE | SAP | planned | agent-058-project-job-costing-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
PUBLIC COURSE DISCOVERY & VETTING | uc-099-public-course-discovery-vetting | PUBLIC COURSE DISCOVERY & VETTING — automation use case managed by PUBLIC COURSE DISCOVERY & VETTING AGENT. | HR | LEARNING & DEVELOPMENT | SAP | planned | agent-059-public-course-discovery-vetting-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "POWER AUTOMATE"] |  | 0 | 0 | 0.16 |  |  |  | null
DOCUMENT VERIFICATION AGENT FOR NEW TALENT | uc-100-document-verification-agent-for-new-talent | AI VALIDATES AND EXTRACTS DATA FROM CANDIDATE DOCUMENTS (IDS, CERTIFICATES) AND AUTO-UPDATES RECORDS | HR | TALENT ACQUISITION | SAP | planned | agent-060-recruitment-data-integrity-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 327 | 90 | 0.27 |  |  |  | null
OFFER & APPROVAL ORCHESTRATOR | uc-101-offer-approval-orchestrator | AUTOMATED OFFER GENERATION, VALIDATION, AND MULTI-LEVEL APPROVAL ROUTING INTEGRATED WITH HR POLICIES AND SAP | HR | TALENT ACQUISITION | SAP | planned | agent-061-recruitment-transaction-orchestration-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 327 | 60 | 0.49 |  |  |  | null
RECONNECTION QUERY SERVICE IMPROVEMENT | uc-102-reconnection-query-service-improvement | RECONNECTION QUERY | Billing | CONNECTION/RECONNECTION | SAP | live | agent-062-remote-connectdisconnect | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 0 | 80 | 0 |  |  |  | null
REMOTE CONNECT/DISCONNECT | uc-103-remote-connectdisconnect | BILLING | Billing | CONNECTION/RECONNECTION | SAP | planned | agent-062-remote-connectdisconnect | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
REMOTE CONNECT/DISCONNECT | uc-104-remote-connectdisconnect | BILLING | Billing | CONNECTION/RECONNECTION | SAP | live | agent-062-remote-connectdisconnect | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Transactions | 7200 | 0 | 0 |  |  |  | null
REVENUE PROJECTION AGENT | uc-105-revenue-projection-agent | BILLING | Billing | PREDICTIVE METER, ANOMALY DETECTION AND READING | SAP | planned | agent-063-revenue-projection-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
RISK SEGMENTATION AND EARLY WARNING | uc-106-risk-segmentation-and-early-warning | BILLING | Billing | PRO-ACTIVE RISK SEGMENTATION | SAP | planned | agent-064-risk-segmentation-and-early-warning | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
KIOSK SERVICES TO SMART OFFICE | uc-107-kiosk-services-to-smart-office | GARTUITY, WARNING,COMPENSATION HISTORY,EMPLOYMENT HISTORY, DRESS CODE, MY TRAINING AND SEMINARS TO BE DEVELOPED IN SMART OFFICE | HR | HR SELF SERVICE | SAP | live | agent-065-sap-automation | 2025-09-01 | 2026-01-01 | 2026-01-01 | 2026-09-01 | ["SAP"] | Device | 15 | 0 | 0 |  |  |  | null
RESUME SCREENING PLATFORM | uc-108-resume-screening-platform | AI SCREENS APPLICANT PROFILES AND SHORTLISTS CANDIDATES BASED ON PREDEFINED ELIGIBILITY CRITERIA AND HIRING MANAGER INPUTS | HR | TALENT ACQUISITION | POWER AUTOMATE | pipeline | agent-066-screening-agent | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["POWER AUTOMATE"] |  | 3000 | 60 | 1.84 |  |  |  | null
SMART DISPATCHER | uc-109-smart-dispatcher | BILLING | Billing | SMART SCHEDULING | SAP | pipeline | agent-067-smart-dispatcher | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
SMART SCHEDULER | uc-110-smart-scheduler | BILLING | Billing | SMART SCHEDULING | SAP | pipeline | agent-068-smart-scheduler | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
STAFF PAYMENTS | uc-111-staff-payments | STANDARDIZE AND STREAMLINE STAFF-RELATE DISBURSEMENTS TO REDUCE MANUAL PROCESSING AND IMPROVE CONSISTENCY | Finance | STRAIGHT-THROUGH FINANCE PROCESSING | SAP | planned | agent-069-staff-payments-operations-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null
RATE CATEGORIES FOR ELECTRICITY AND WATER. | uc-112-rate-categories-for-electricity-and-water | BILLING | Billing | CUSTOMER 360 | SAP | planned | agent-070-the-system-automatically-determines-and-assigns-the-correct- | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 6000 | 0 | 0 |  |  |  | null
TRAINING COST RECOVERY CALCULATION | uc-113-training-cost-recovery-calculation | TRAINING COST RECOVERY CALCULATION — automation use case managed by TRAINING COST RECOVERY CALCULATION AUTOMATION. | HR | LEARNING & DEVELOPMENT | SAP | planned | agent-071-training-cost-recovery-calculation-automation | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0 |  |  |  | null
TRAINING IMPLEMENTATION | uc-114-training-implementation | TRAINING IMPLEMENTATION — automation use case managed by TRAINING IMPLEMENTATION & COMMUNICATION ORCHESTRATION AGENT. | HR | LEARNING & DEVELOPMENT | SAP | planned | agent-072-training-implementation-communication-orchestration-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 2.16 |  |  |  | null
TRAINING NEEDS CONSOLIDATION | uc-115-training-needs-consolidation | TRAINING NEEDS CONSOLIDATION — automation use case managed by TRAINING NEEDS CONSOLIDATION & VALIDATION AGENT. | HR | LEARNING & DEVELOPMENT | SAP | planned | agent-073-training-needs-consolidation-validation-agent | 2026-06-01 | 2026-10-01 |  | 2027-06-01 | ["SAP"] |  | 0 | 0 | 0.1 |  |  |  | null
VENDOR BANK DETAIL CHANGE REQUESTS | uc-116-vendor-bank-detail-change-requests | REDUCE PROCESSING TIME AND MANUAL HANDLING FOR MANAGING VENDOR BANK DETAIL REQUESTS. | Finance | CONTRACTS FACILITATION | SAP | pipeline | agent-074-vendor-bank-detail-change-request-automation | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "RAMMAS"] |  | 0 | 0 | 0 |  |  |  | null
WORKLOAD PLANNER | uc-117-workload-planner | BILLING | Billing | SMART SCHEDULING | SAP | pipeline | agent-075-workload-planner | 2026-01-01 | 2026-05-01 |  | 2027-01-01 | ["SAP", "AI ENGINEERING"] |  | 0 | 0 | 0 |  |  |  | null